## Slide 1: Project Management : Techniques and Tools (60-499)
Fall 2014 / Winter 2015

## Slide 2: Who are the stakeholders?
Clients/Customers
Upper Management
Project Manager
Developers/Workers

## Slide 3: A project manager’s role
A major role of a project manager (PM) is to ensure that the project succeeds
  To a lesser degree, this is also a role for other stakeholders
Therefore, the PM is responsible (if not to blame) when these problems occur
A project manager must remain unbiased
  Customers or upper management may ask for unrealistic features and/or schedules
  It is not a project manager’s role to make such schedules work, by pushing developers harder

## Slide 4: What would you look for in a PM?
sufficient experience
  has experienced successful projects
  has experienced failed projects
has excellent organizational skills
has excellent communication skills
is a strong leader
project management certifications:
  Project+: Entry-level certification, for aspiring project managers
  PMP: Professional cert., for experienced project managers
    Project management body of knowledge (PMBOK)

## Slide 5: Project Management Phases
1. Defining
2. Risk Management
3. Planning & Scheduling
4. Launching
6. Closing
5. Monitoring & Controlling

## Slide 6: Defining
Determine what the customer wants
Identify Requirements
  Goals
  Deliverables
  Success criteria
Scope

## Slide 7: Goals
A goal is normally a solution to a problem
When defining goals, answer the following questions:
  What problem will we solve?
    e.g. Accounting department has 2 month turnaround for budget requests, which is too long.
  In what sense will we solve the problem?
    e.g. Our accounting software will streamline the process of budget re-work.
May be made of smaller sub-goals

## Slide 8: Deliverables
Deliverables are the actual artifacts created by the project team for the customer
These typically include:
  Binary packages
  Source packages (in open source projects)
  Documentation & tutorials
  Version history
  Utilities
  Installation software

## Slide 9: Success Criteria
Success criteria define what must be true in order for the project to be considered a success
  related to the goals
  attributes that can be measured
    e.g. The accounting department’s time to approve a budget is reduced by at least 50%.

## Slide 10: Scope
The project’s scope defines its boundaries
  Closely related to the Requirements
  PM may work with customers to decide which requirements are necessary, and which are not
  Determine whether or not a feature request (change) is appropriate later
Thus, scope deals with both requirements and changes

## Slide 11: Risks
Risks are things that could cause the project to:
  Fail
  Be delayed
  Require additional budget
  Require additional personnel
A project manager should identify:
  Impact: What is the expected negative impact should it occur?
  Probability: How likely is it to occur?

## Slide 12: Risk Document
The risk document:
  Identifies and describes risks
  Describes what conditions make it happen
  Describes the probability of it happening
  Describes the impact of it happening
  Describes a plan for how to (try to) avoid it happening
  Describes a plan for what to do if it happens
    This is only done if the probability and/or impact necessitate such a plan

## Slide 13: Planning
We know what we want and the associated risks
Now, we figure out how to do the work required
We do this by:
  Performing architecture & design
  Identifying activities: work breakdown structure (WBS)
  Identifying dependencies between activities
  Estimating activity duration
  Estimating activity resource requirements
  Scheduling activities (start date, duration)

## Slide 14: Architecture & Design
Architecture: Refers to the overall structure of the application - defines the modules
  Each module has a set of common responsibilities
Design: Refers to the structure of the module itself
  Can involve creating classes (in OOD) and assigning responsibilities (functions or data) to them

## Slide 15: Activities
An activity is something a participant may undertake
  This could be:
    Designing a module
    Updating documentation
    Optimizing the search code
    Installing the binaries in a web server
    Writing a lookup method
Activities can be:
  Estimated for time & resource requirements
  Assigned to team member(s)

## Slide 16: Schedule
A schedule is a time-plan for activities
The schedule must:
  Include all activities
  Show dependencies between activities
    e.g. What must occur before this activity can start?
  Show estimated durations for activities
  Show starting points for activities
  Show combined activity duration as project duration
  Show estimated resources for activities
  Show combined activity resource requirements as project resource requirements

## Slide 17: Work Breakdown Structure
The WBS:
  Defines all activities
    Each system function is defined as a high-level activity
    Each activity is broken down into smaller activities
    This process repeats until activities are small and manageable
  Shows hierarchical relationships between activities
    A WBS can be represented with a tree diagram

## Slide 18: Project Plan
The project plan defines:
  Dependencies between activities
    e.g. Architecture must be determined before development can begin
  Schedule
    Including an estimate of each activity’s duration
  Initial activity assignment
    Activities are assigned to fictitious team members

## Slide 19: Launching
We have a detailed work plan
Now, we get the work underway
We do this by:
  Choosing participants
  Making participants available for the project
  Assigning work to participants
  Organizing participants into team(s)
  Providing resources to the team(s)
  Establish constraints and freedoms for the team(s)

## Slide 20: Monitoring & Controlling
We have people working on activities
Now, we must ensure we are making adequate progress
We do this by:
  Interviewing and observing progress reports
  Implementing version control software
  Providing mechanisms for requesting changes
  Continually updating plans (e.g. schedules)

## Slide 21: Closing
We have completed all activities
  The result should be that
    All overall goals are satisfied
    All success criteria are met
    All deliverables are ready for roll-out
Now, we need to complete hand-over
We do this by:
  Obtaining client acceptance
  Deploying deliverables
    e.g. media disks, printed manuals, online deployment/downloads
  Performing a post-mortem analysis
    How did we do?

## Slide 22: Post-Mortem Analysis
A post-mortem involves analyzing the project upon completion
  This is not to be confused with QA, which analyzes the deliverables
A post-mortem is a critical step, that many project managers miss
  May allow the manager to
    More accurately estimate activities after the experience
    Identify mistakes made, to avoid making them again
    Recognize personal achievements

## Slide 23: Summary
Project management’s job is to ensure that projects do not fail
  We must identify what the customer wants
  We must identify potential pitfalls
  We must list what needs to be done
  We must make detailed plans
  We must prepare for changes
  We must ensure that our plans are being followed
  We must ensure that our plans are working
    If not, we must update them or take another corrective action