## Slide 1: Why do projects fail?
% of commercial projects fail. % of open source projects fail.
90
80

## Slide 2: Why do projects fail?
We need to ask these important questions:
  What kind of failure was it?
    e.g. incomplete, unreliable, off-schedule/budget
  Who was responsible?
  What happened or did not happen?
  Which process(es) broke down?
  What module(s)/feature(s) failed?

## Slide 3: Project Management Phases
1. Defining/Requirements
2. Risks
3. Planning & Scheduling
4. Launching
6. Closing
5. Monitoring & Controlling
Built the wrong thing
Ignored potential pitfalls
Overly optimistic schedules
Poor team dynamics
Poor development practices
No customer acceptance

## Slide 4: Who is responsible?
Developers?
    Poor design
    Uncommitted or de-motivated developers
    Silver bullet syndrome
    Lack of source control, abandoned planning
Client/Upper management?
    Feature creep
    Unrealistic schedules
    Unrealistic expectations
    Incorrect requirements
Project Manager?
    Poor planning
    Insufficient risk management
    Insufficient quality assurance

## Slide 5: Case Study 1: ATCSoft
The ATCSoft project was launched, and steady progress was made
When the team set out to integrate the ATCSoft application with existing RADAR equipment, however, they hit a snag
  The team members could not figure out how to integrate the systems
    The RADAR system did not have appropriate physical connections, nor was there an appropriate driver for the interconnection
  The project manager had to hire engineering consultants to work out the integration details
  This diversion took 2 months and cost a significant amount of money (additional labour, consultancy fees, and business value)

## Slide 6: What happened?
  A technical problem ended up stalling development
    This could easily have become a complete disaster, if it were not possible to integrate the systems

## Slide 7: Case Study 2: PathFinder 2.0
The PathFinder project was started in August
  Rory T. was the star developer
    His knowledge of neural nets inspired him to suggest that a neural net implementation of a PathFinder would be a good idea
    He wrote up much of the foundation code for the neural network
    Initial tests showed a definite improvement in the PathFinder performance, and more realistic, human-like, decisions
  Despite the large salary increase he was offered, Rory took a good offer with another firm
    When some tests showed that the neural net was not fast enough to make real-time decisions, the team had no immediate answers
    A bug was found that sent the avatars wandering aimlessly around the maze in a circuit, when certain rare conditions were present
    Again, the team had no idea how to approach the problem

## Slide 8: What happened?
  A personnel problem was at fault
    The team’s over-reliance on a single person was their downfall
    Taking him out of the equation stalled development
  In both cases, the team neglected their risks
    It is critical for a project team to understand and plan for risks

## Slide 9: Risk Mitigation
In ATCSoft project: the team should have investigated the integration of various systems at the start of the project
  Given adequate time, the integration could have been worked out before it was needed
In the PathFinder project
  Rory could have thoroughly documented the neural network code as it was developed
  He could have had seminars for team members, explaining the concepts of neural networks
  Understanding neural networks, the team would have a better chance of carrying on without Rory

## Slide 10: Risk Assessment
The following describes the risk assessment process:
Once risks are assessed, a project manager should plan for them
1. Identifying risks
2. Estimating a risk’s cost/effects
3. Estimating a risk’s likelihood
4. Identifying alternatives
5. Evaluating/comparing alternatives

## Slide 11: Risk Identification
The first step in risk analysis is to identify the project’s risks
  Each project has its own set of unique risks
Identifying risks seems like a dark art
  How do you identify something that could potentially be hidden until it is too late?
  Risk identification can be made easier using categories of risk
    This leverages the knowledge of many project managers who have experienced risks

## Slide 12: Categories of Risk
  Technical risks (related to using a particular technology)
    Performance
    Reliability
    Availability
    Complexity
  Project management risks
    Poor resource allocation
    Poor planning
    Poor prioritization
  Organizational risks
    Lack of support or resources
    Inadequate or inefficient management
    Interference from other projects & management agendas

## Slide 13: Categories of Risk
  Constraint risks
    Deadlines
    Resources
  Business risks
    Marketability
    Timing
    Vendor delays
    Economic conditions
  External risks
    Changing laws and regulations
    Dependence upon suppliers and contractors

## Slide 14: When do we identify risks?
  Identify risks before the planning phase
    Some risks may be difficult to spot when looking at requirements at a high level
  Identify risks after the planning phase
    It is useful to know risks before the planning phase, so that extra time can be dedicated to their mitigation
A good compromise is to perform risk identification during the planning phase:
  After creating the work breakdown structure
  Before creating the schedule

## Slide 15: Common Risks
  Feature creep
    New features are frequently added after development has started
  Implementation gold-plating
    Developers are working on the perfect implementation
  Inadequate design
    Too little attention has been paid to design
  Overly optimistic schedules
    Management pushed schedules down, rather than schedules work their way upward from developers
  Poor motivation/weak personnel
    Developers are working at a less-than-optimal pace
  Silver-bullet syndrome
    A trendy technology was expected to produce the equivalent to 10,000 lines of code in only 50 lines of code
  Contractor failure
    A contractor lacked expertise/commitment needed to do the job on schedule

## Slide 16: Estimating Risk Costs & Effects
Estimating the costs & effects of a risk is dependent upon the risk
  e.g. A project using a new technology might realize that the technology is inadequate or unreliable
    Now, the application must be retrofitted to another (trusted) technology
    Much of the software may need to be replaced
    The cost in this case is the cost of developing the obsolete components
    In addition, there may be hidden costs due to delays (such as customer confidence or personnel availability)

## Slide 17: Estimating Risk Costs & Effects
Estimating the costs & effects of a risk is dependent upon the risk
  e.g. In some projects there is a risk that a key developer will leave the project
    If the key developer leaves, what will it take to replace her?
    Given market conditions, you might estimate a replacement in 2 months
    Some project deliverables might be delayed by up to that amount in her absence
    Also, you may have to consider signing bonuses, relocation expenses, travel expenses, and other hiring costs
    It depends on the project whether or not these costs are considered high

## Slide 18: Estimating Risk Likelihood
Like risk cost, risk likelihood also depends on the risk
  The likelihood that a technology will fail can usually be estimated accurately, e.g.
    Based on performance in similar projects
    Based on performance in “well-known” projects
    Based on available expertise
  Other types of risks e.g. likelihood of a person leaving a project may be harder to quantify
    One possibility is to ask

## Slide 19: Identifying Alternatives
C++ or Java?
If Sarah leaves, who can replace her?

## Slide 20: Evaluating & Comparing Alternatives
Let us examine alternatives to Sarah:
  Gerard: Has leadership, but lacks the technological expertise
    Gerard is a take charge kind of person
    He is also a get it done kind of person
    However, he is not familiar with XML and many other technologies we plan to use
  Helen: Knows some of the technology, but is very inexperienced
    Helen knows XML and a few other technologies we plan to use
    However, Helen is just starting her career
    She has difficulty being assertive and taking charge
    She doesn’t command respect from her colleagues
    Her development itself is slow