## Slide 1: Work Breakdown Structures
Identifying Manageable Activities

## Slide 2: Agenda
1. Creating a WBS
2. Using the WBS for Estimation

## Slide 3: Work Breakdown Structure
Work
  A WBS considers the work that needs to be performed
  This includes development, but also user manuals, sales support, administration, deployment, media, etc.
Breakdown
  Work is broken down (decomposed) into small pieces (activities)
  Activities are eventually broken down into tasks
  A task is something that takes less than a week to complete
  Activities are normally assigned to individuals
Structure
  Each unit of work is broken down into a number of components
  The result is a hierarchical structure
  The lowest layers are tasks
    e.g. A function that generates a polynomial collision-handling hash function is completed
    e.g. Send user manual prototype to printer for an estimate
  The middle layers could be milestones
    e.g. “Getting started” tutorial is completed
  The highest layers are normally deliverables
    e.g. Source code distribution, with configuration and makefiles, is completed

## Slide 4: Terminology
Activity:
  Some behaviour that needs to be done
  Produces some outcome (e.g. a deliverable)
  Is often decomposed into other activities or tasks
Task:
  An activity that is not decomposed
  Is at the lowest level of the WBS
  Also called a work package

## Slide 5: Advantages of a WBS
The WBS:
  Gives you a somewhat complete list of tasks
    Later, this can be a checklist to show how much is still to be done, and how much is done
  Allows you to easily assign work to team members
  Requires you to solidify things that are still vague, even after requirements analysis
    Generating a WBS enables you to methodically decompose the work, exposing new risks and resource requirements

## Slide 6: WBS Process Overview
The WBS process is basically as follows:
  The WBS is normally created from the top down
  The estimates are created at the bottom
  The estimates are summed from the bottom up
  The totals at the top are used as input for the schedule

## Slide 7: Creating a WBS: Top-down
The top-down approach:
  Start with the project’s overall goal
  Decompose the goal into deliverables
  Decompose the deliverables into modules
  …
  When you are finished you have tasks
    Tasks should be a few days work or less
It is a good idea to create the WBS as a group
  This can prevent important activities from being missed, and can add a level of peer evaluation to the process

## Slide 8: When is a WBS done?
Since WBS is iterative, it could go on forever
There are guidelines for what is enough:
  Status/completion is measurable
  The activity/task is bounded
  The activity/task has a deliverable
  Time and cost are easily estimated
  Activity/task duration is within acceptable limits
  Work assignments are independent

## Slide 9: Status/Completion is Measurable
Project managers will ask team members about status
  Status is generally how close they are to completion
Activities:
  Status of an activity is the ratio of completed tasks
    e.g. I’m finished 35 of 55 tasks, so I’m 64% done
  Completion of an activity is when all of its tasks are complete
Tasks
  Status of a task is generally small enough to estimate
    e.g. I’ve written all the code for the class, and just need to test it, so I’m about 50% done
  Completion of a task should take a few days or less

## Slide 10: The Activity/Task is Bounded
The starting and ending points of an activity should be well-known
  How do you get started on the activity? What task to do first?
  How do you finish the activity? What is the last task to be done?
e.g. Optimize the search engine
  Tasks:
    Determine from customers the expected wait time
    Measure existing search engine for comparison
    Examine code for potential slowdowns
    Make changes where possible
    Investigate compiler options which could improve performance
    Update build file to use new compiler options
    Deploy search engine to test server
    Measure new search engine performance
    Verify that search engine meets customer criteria
    Deploy search engine in public server
    Ask customer for review and acceptance

## Slide 11: The Activity/Task Has a Deliverable
All activities should produce something
  High-level activities produce the deliverables outlined in the requirements
    e.g. Source code distribution, user manual, DVD media
  Lower-level activities can produce other ‘deliverables’
    e.g. AI engine, device API for bar code readers, a customer class

## Slide 12: Time & Cost are Easily Estimated
The less work is involved in an activity, the easier it is to estimate
When we get down to task level, it should be possible to accurately estimate time and cost
  Time: It is less work, so estimates should be accurate, particularly when the task is similar to something else done recently
    e.g. Write the code to manage persistence of customers to/from the database
      This is similar to other persistent code you have (or will) write, so can be accurately estimated
  Cost: You will know if there are additional costs required
    e.g. Licenses for an IDE, books, training
We’ll deal with estimation separately

## Slide 13: Activity/Task Duration is Within Acceptable Limits
Activities can take a very long time
However, tasks (the lowest level of decomposition) should be limited in duration
  Generally, less than 1-2 weeks is considered acceptable
This is something that can be easily tracked
Also, if something goes wrong, things should not go to far off track
  e.g. A 5 day task takes 7 days to complete
  e.g. A 10 day task was a waste of time, and needs to be re-thought

## Slide 14: Work Assignments are Independent
When a task is assigned to a team member, it should be possible for that team member to complete without further instructions
  e.g. A team member should not be meeting daily with a manager or customer while working on a 10 day task
A team member working on a task should have all they need when they begin
  A team member building on another task’s deliverables should start the task after the other task’s deliverable is ready
  e.g.
    A team member is working on improving the design for the 3D graphical engine
    When this is complete, another programmer might want to incorporate her code into the graphics engine
    This should not be done until the graphics engine is complete (with respect to the re-design)

## Slide 15: Common Sense with WBS
Another way to ensure a WBS is complete is to use common sense
If you were to tell a young child to brush their teeth, they might need more detailed instructions
  Get your toothbrush and the toothpaste
  Put a little bit of toothpaste on the toothbrush
  Brush the front, back, tops, bottoms, and sides of your teeth
  Spit into the sink
  Rinse out your mouth with some water
  Put away the toothbrush and toothpaste
However, team members have done similar tasks before
  If you say brush your teeth to an adult, they know what to do
    Not only is it a waste of time to go into more detail, it is also insulting
    This is called micromanaging

## Slide 16: Estimation
Estimation involves using the following information in order to make an educated guess about time or resource requirements:
  Knowledge of the work required (expertise)
    Ask people who know how long it should take
  Group knowledge
    Coming up with estimates as a group is no substitute for expertise, but sometimes expertise is not available
    Advice from a group is generally more reliable than advice from an individual
  Prior experience
    e.g. It previously took 8 minutes to copy, print, seal, stamp, and address 1000 brochures
    It should take about 80 minutes to get 10,000 brochures ready
  Historical data
    e.g. The team has worked on 3 other projects, which were all 25-50% over-budget on time
    Therefore, expect them to go over their own estimates by a similar factor

## Slide 17: Estimation Units
There are several units in estimation:
  Total time
    e.g. It should take 3-4 weeks, with a most likely estimate of 18 days
    This makes it obvious when the project should be completed
  Human resource utilization (effort)
    e.g. It should take 2-3 person-months, with a most likely estimate of 10 person-weeks
    This way, you can see how adding people to the project will affect its duration
  Lines of code (size)
    e.g. It should be around 50,000 lines of code
    This figure can then be used for other estimates, such as total time
    However, few developers count lines of code anymore, so this is not very common
    Also, not all lines of code are created equal
  Function points (size/difficulty)
    An estimate of the number of inputs, outputs, files, database tables, etc. that an application will require
    e.g. This should have 6 inputs of low complexity (x3), 2 inputs of medium complexity (x4), and … for a 286 function point score

## Slide 18: What is a schedule?
A schedule is a description of start and end times for all the WBS’ tasks
  The schedule accommodates the plan
  The schedule specifies all dates in terms of offsets from the start date
  Ideally, the start date is a parameter which can be changed if the project start is delayed
    This way, real dates can be seen
    However, dates are not hardcoded so they can be easily changed
An important part of the schedule is the Gantt chart

## Slide 19: Network Diagram
A network diagram shows task/activity flow
Flow from one task to another may indicate:
  Dependencies between the tasks
  Chronological ordering between the tasks
Parallel task flows indicate task independence
  It is not necessarily the case that tasks may be done in parallel, but it is possible
  Example :
Begin
End

## Slide 20: Schedules
A schedule is an implementation of the project plan
  However, in industry lingo, a project plan document normally includes the schedule
A common schedule representation is a Gantt chart
  A Gantt chart is a graphical depiction of the task flow, with dates
  Dates are shown as the x-axis, so questions about start/end times can be answered
    e.g. Relative start times of parallel tasks
    e.g. Completion of all of an activity’s tasks
    e.g. Chronological dependencies between tasks
However, other formats are possible:
  A calendar, showing tasks started, active, and completing
  A list of task descriptions, including start and expected end dates

## Slide 21: Gantt Charts
Visual representation can help when a project manager needs an overview:
September
October
November
December
User Interface
Prototype
Registration
Persistence
Code to Gen.
Password MD5
…etc…
Registration
Dialog
…etc…

## Slide 22: Common Schedule Problems
Problems with estimates or deadlines:
  Customer or upper management set deadline without team consultation
  Schedule is based on ‘best case’ estimates
  Target date moved up without re-adjustment to scope, resources, or schedule
Problems with requirements:
  Schedule omits necessary tasks
  Project size is impossible within allotted time
  Project is larger than estimated
  Effort is greater than estimated
Problems with schedule management:
  Schedule was based on specific team members that will not be available
  Schedule slips are ignored when schedule is re-evaluated (velocity)
  Delays in tasks result in delays in dependent tasks
  Unfamiliar territory causes unexpected delays
Problems with productivity:
  Demotivated personnel (e.g. schedule pressure)
  Weak personnel
  Friction between team members